## Sheet1
 | time axis 2019-06-07 to 2019-07-21
| Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
| 1st meeting |  |  |  | Proposal report and presentation |  | 2nd meeting | [7 empty] | 3rd meeting | [9 empty] | 4th meeting |  |  |  | 5th Meeting | Final Presentation | [14 empty] | Report DDL
Content | 2019-06-07: Kick-off meeting 1: understand overall goal of the project 2. Split 80 factors into 4 sub-groups for analysis; 2019-06-11: 5% of total grade; 2019-06-13: Shared single factor analysis results To do list: 1. Data Observation and Cleaning (all members) 2. Update single factor analysis based on the given format (all members) 3. Feature engineering: to read kennels and replicate it, to rank all the variables according to their explanatory power (link: https://www.kaggle.com/massquantity/all-you-need-is-pca-lb-0-11421-top-4 ) 4. Regressional analysis iteration one_DDL 21 June; 2019-07-01: Share report wording tec.; 2019-07-05: 1. repalce mode() with median()